## Instructions
ITC327W Project Progress and Contribution Workbook
Use this workbook throughout the semester. Update it after each project phase and submit the same workbook again so that progress can be tracked over time.
Sheet | Purpose | Evidence and Accountability Rules
Project Overview | Enter the group and project details. The dashboard summarises task progress automatically. | 1 | Every student must be assigned meaningful work in Microsoft Project.
Task Progress | Record planned and completed tasks, responsible students, dates, status, percentage completed and evidence. | 2 | Completed work must be supported by evidence such as GitHub activity, meeting records, document sections, screenshots or stakeholder communication.
Individual Contributions | Record the work personally completed by each student. Every entry must have evidence. | 3 | GitHub commits are not the only evidence. Planning, interviewing, documentation, coordination and quality review also count.
Stakeholder Engagement | Record meetings, calls and emails with the stakeholder and the main outcomes. | 4 | Do not record work as completed by a student when it was completed by someone else.
Challenges & Actions | Record project challenges, their effect and the corrective action taken. | 5 | Do not place passwords, API keys, identity numbers, private contact details or confidential records in this workbook or on GitHub.
Phase Summary | Provide a short summary of the phase, including achievements, outstanding work and participation concerns. | 6 | The confidential individual peer evaluation must be completed separately on Blackboard.
Group Reflection | Complete one shared reflection after each phase. Be honest and specific.
Recommended Update Points
|  | Unit 1 / Phase 1 | Planning, stakeholder engagement, requirements and initial SRS
|  | Phase 2 | Architecture, UML, ERD and interface design
|  | Phase 3 | Development, integration, testing and demonstration
|  | Final | Overall project summary and final reflection

## Project Overview
Project Overview and Progress Dashboard
Project Information | Group Response | Task Status | Count
Group name or number | TechWizards | Completed | 14
Project title | Student Accommodation System | In Progress | 0
Stakeholder or organisation | Butis Bloc | Not Started | 0
Group mentor | MR MOKODUWE | Delayed | 0
Reporting phase | Unit 1 / Phase 1 | Blocked | 0
Reporting period | 2026-08-23 | Overdue | 0
Overall status | In Progress
Overall % complete | 93.33% | Contribution Summary | Count
Main achievement | Completion of the planning and requirement analysis for the system | Contribution entries | 7
Main challenge | Adjusting to new members in our group and aligning on how we work together | Verified entries | 7
Next planned activity | Commence with the system design and codding phase | Unverified entries | 0
|  | Stakeholder engagements | 1

## Task Progress
Task Progress Tracker
Task ID | Reporting Phase | Activity | Task Description | Assigned Student(s) | Start Date | Due Date | Status | % Complete | Evidence / Link | Verified by Group | Lecturer Comment | Progress Flag
U1-01 | Unit 1 / Phase 1 | Activity 1.1 | Identify and confirm the external stakeholder | Michell Kgatuke | 2026-08-18 | 2026-08-25 | Completed | 100 | Communicated via Email | Yes |  | Completed
U1-02 | Unit 1 / Phase 1 | Activity 1.1 | Document the current process and problem | Chauke Salgah | 2026-08-20 | 2026-08-25 | Completed | 100 | Progress report and microsoft project are proof | Yes |  | Completed
U1-03 | Unit 1 / Phase 1 | Activity 1.1 | Define the project aim, objectives and scope | Michell Kgatuke | 2026-08-20 | 2026-08-25 | Completed | 100 | Documentation was sent on group whatsApp | Yes |  | Completed
U1-04 | Unit 1 / Phase 1 | Activity 1.2 | Prepare stakeholder interview questions | Kananelo Mafohla | 2026-08-20 | 2026-08-25 | Completed | 100 | Documentation was sent on group whatsApp | Yes |  | Completed
U1-05 | Unit 1 / Phase 1 | Activity 1.2 | Conduct and document the stakeholder interview |  | 2026-08-20 | 2026-08-28 | Completed | 100 |  | Yes |  | Completed
U1-06 | Unit 1 / Phase 1 | Activity 1.3 | Compile the initial SRS | Michell Kgatuke | 2026-08-20 | 2026-08-25 | Completed | 100 | Documentation was sent on group whatsApp | Yes |  | Completed
U1-07 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Microsoft Project schedule | Manala Elelwani | 2026-08-20 |  | Completed | 100 | Documentation was sent on group whatsApp | Yes |  | Completed
U1-08 | Unit 1 / Phase 1 | Activity 1.3 | Create and configure the GitHub repository | Thato Malepe | 2026-08-20 | 2026-08-25 | Completed | 100 | https://github.com/MalepeMM/student-accommodation-management-system | Yes |  | Completed
U1-09 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Supabase project | Thato Malepe & Chauke Salgah | 2026-08-20 | 2026-08-25 | Completed | 100 | https://github.com/MalepeMM/student-accommodation-management-system | Yes |  | Completed
U1-10 | Unit 1 / Phase 1 | Activity 1.3 | Complete the progress report and contribution record | Phumla Mongwe | 2026-08-20 | 2026-08-25 | Completed | 100 | Group members verified it | Yes |  | Completed
U1-11 | Unit 1 / Phase 1 | Activity 1.3 | Complete the Unit 1 group reflection | phumla Mongwe | 2026-08-20 | 2026-08-25 | Completed | 100 | Group members verified it | Yes |  | Completed
U2-01 | Unit 2 / Phase 1 | Activity 2.1 | Evaluate feasibility | VP Mashele | 2026-08-20 | 2026-08-25 | Completed | 100 | Documentation was sent on group whatsApp | Yes |  | Completed
U2-02 | Unit 2 / Phase 1 | Activity 2.2 | Identify ,assess and plan for project risk | VP Mashele | 2026-08-20 | 2026-08-25 | Completed | 100 | Documentation was sent on group whatsApp | Yes |  | Completed
U2-03 | Unit 2 / Phase 1 | Activity 2.3 | Applying the findings and refine the project | M Kgatuke | 2026-08-20 | 2026-08-31 | Completed | 100 | Documentation was sent on group whatsApp | Yes |  | Completed
Formulas:
Progress Flag = IF([Task Description]="","",IF([Status]="Completed","Completed",IF([Status]="Blocked","Blocked",IF([Status]="Delayed","Delayed",IF(AND([Due Date]<>"",[Due Date]<TODAY(),[Status]<>"Completed"),"Overdue","On Track")))))

## Individual Contributions
Individual Contribution Record
Student Name | Student Number | Reporting Phase | Activity | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Notes
Phumla mongwe | 222072446 | Unit 1 / Phase 1 | Activity 1.3 | Group reflection & progress report and contribution record | All allocated task were completed | 2026-08-23 | 8 | Document was sent on whatsapp group | Yes | 2026-08-25 | N/A
Kananelo Mafohla | 223038263 | Unit 1 / Phase 1 | Activity 1.2 | Prepare stakeholder interview questions | All allocated task were completed | 2026-08-21 | 1 | Document was sent on whatsapp group | Yes | 2026-08-25 | N/A
Michell Kgatuke | 222029835 | Unit 1 / Phase 1 | Activity 1.1 & 1.3 | Compile the initial SRS, identify and confirm the stakeholder | All allocated task were completed | 2026-08-25 | 12 | Document was sent on whatsapp group | Yes | 2026-08-25 | N/A
Thato Malepe | 223015611 | Unit 1 / Phase 1 | Activity 1.3 | Created Github repository and supabase project | All allocated task were completed | 2026-08-20 | 1 | https://github.com/MalepeMM/student-accommodation-management-system | Yes | 2026-08-25 | N/A
VP Mashele | 224120975 | Unit 2 / Phase 1 | Activity 2 | Evaluate feasibility Identify ,assess and plan for project risk Apply the findings and refine the project | All allocated task were completed | 2026-08-22 | 12 | Document was sent on whatsapp group | Yes | 2026-08-25 | N/A
Salgah Chauke | 223032277 | Unit 1 / Phase 1 | Activity 1.3 | Created and supabase project , and document current process and problems | All allocated task were completed | 2026-08-20 | 2 | https://github.com/MalepeMM/student-accommodation-management-system | Yes | 2026-08-25 | N/A
Manala Elelwani | 222057458 | Unit 1 / Phase 1 | Activity 1.3 | Create Microsoft Project schedule | All allocated task were completed | 2026-08-25 | 5 | Document was sent on whatsapp group | Yes | 2026-08-25 | N/A

## Stakeholder Engagement
Stakeholder Engagement Record
Date | Reporting Phase | Type of Engagement | Purpose | Students Present | Stakeholder Present / Role | Main Findings | Action Required | Evidence / Link
2026-08-28 | Unit 1 / Phase 1 | Email | Iderstand the current system, Identify challenges, gather requirements, defining scope and objectives and build professional relationship | Salgah chauke Michell kgatuke VP mashele | Guide system objectives and validate that the student accommodation management system addresses real operational challenges | Student accommodation is currently managed through untrusted and fragmented channels such as WhatsApp, Facebook, telephone calls, paper records and spreadsheets. These methods make it difficult for landlords to keep accommodation listings, student enquiries, student information and maintenance requests organised in one place. | Document all requirements , analyze current challenges,define system objectives and scope, and prepare for the design phase after stakeholder validation | Email communication
The problem affects both landlords and students. Landlords may lose track of enquiries and important documents including lease agreements, while students may experience delays when searching for available accommodation or submitting requests, and may be scammed by fake landlords. The lack of a centralised system results in lost information, duplicated communication, delayed responses and inefficient accommodation management.
An integrated digital solution is therefore needed to centralise accommodation information, student applications and maintenance requests, and to improve communication between landlords and students

## Challenges & Actions
Challenges and Corrective Actions
Date Identified | Reporting Phase | Challenge | Effect on Progress | Corrective Action | Responsible Student | Target Date | Status
2026-08-23 | Unit 1 / Phase 1 | Delayed feedback from stakeholder | Affected finalizing requirements | improve communication within the group | Michell Kgatuke | 2026-08-25 | Resolved
2026-08-23 | Unit 1 / Phase 1 | Limited experience with microsoft project | lack of the skill left the task incomplete | Allow time to learn microsoft project and complete in in the next phase | Manala Elelwami | 2026-08-25 | Resolved

## Phase Summary
Phase Progress Summary
Summary Information | Group Response | Phase Completion Checklist
Reporting phase | Unit 1 / Phase 1 | Initial or updated SRS completed | Yes
Reporting period | 2026-08-23 | Progress report updated | Yes
Overall phase status | In Progress | Individual contributions recorded | Yes
What was completed during this phase? | Stakeholder identification , scope statement ,questionnairs , set up github and supabase, and feasibility & risk register | Stakeholder engagement recorded | Yes
What remains incomplete? | Microsoft project | Challenges and actions updated | Yes
Why is it incomplete? | Team member had limited access with the software | Group reflection completed | Yes
Which contributions were particularly important? | Stakeholder analysis , requirements gathering and compiling the final documentation | Microsoft Project updated | Yes
Were there participation concerns? | No major participation concerns , all members participated and contributed to the project | GitHub evidence available | Yes
What will the group improve in the next phase? | Early task allocation, better communication and ensuring all required tools are completed | Confidential peer check completed | Yes
Main priority for the next phase | finalizing the system design

## Group Reflection
Group Reflection
Reflection Information | Group Response | Reflection Guidance
Reporting phase | Unit 1 / Phase 1 | Length | Approximately 300–400 words in total.
Project title | Student Accommodation System | Focus | Discuss the group’s actual experience, not the activity instructions.
Most important learning from this phase | Understanding the importance of proper planning and clear stakeholder communication in defining accurate system requirements before starting any development | Honesty | Identifying a genuine challenge will not disadvantage the group when an improvement action is provided.
What went well and why? | Every thing went well because we worked as a team , communicated effectively and clearly divided tasks.This helped us complete all phase 1 deliverables on time | Evidence | Ensure that claims about participation agree with the contribution record, Microsoft Project and GitHub.
What was difficult and why? | Scheduling and coordinating meetings with our external stakeholder and aligning all group members was difficult due to different availability and communication delays | Research use | Student work may only be used for research after the required ethical approval and consent processes.
How were tasks divided among members? | Tasks were decided based on each member's skills and availability , and divided equally during our group meetings to ensure everyone contributes fairly
Did all members contribute fairly? Explain. | Yes all members contributed fairly as tasks were shared equally and each member completed their assigned deliverables on time and supported each other when needed
How did the group handle disagreements or delays? | We handled disagreements and delays through open discussion and voting on the best solution, and by supporting members who were behind to keep the project on track
What did the group learn from the stakeholder? | We learned the real business needs and challenges of stakeholder, which helped us understand the importance of building system that solves actual operational problems and not just technical requirements
Improvement action 1 for the next phase | Improving time management by setting internal deadlines earlier than the official due date to avoid last minutes pressure
Improvement action 2 for the next phase | Enhance communication by having more regular check in meetings and updating each other frequently on progress
Priority for the next phase | To start early on system design and documentation are accurate